## Read Me
The Data Migration Toolkit
WORKED EXAMPLE
What this is | The working sheets for running a data migration end to end, one tab per artefact, in the order you need them.
The eight stages | Kickoff and scope. Profile the source. Map the fields. Clean and de-dupe. The dry run. User acceptance testing. Freeze, cutover and bridge. Hypercare and close. Every stage ends at a gate, and a gate is a stage you do not leave until somebody signs.
THE TABS
Overview | Progress by stage, calculated from the plan.
Migration Plan | The task list. Set Status and % Complete as you go.
Action Log | Every action and decision, with an owner and a date. Your chase list.
Change Requests | Anything asked for that was not in the signed scope. Log it the same day.
Field Mapping | Source field, target field, the rule, and who signed it off.
Exception Sheet | What the cleaning rules could not fix. The client decides each one.
Reconciliation | Counts and control totals, source against target. Run before and after.
Linkage Check | Every document ties to a record. Anything that does not is an orphan.
Gate Sign-off | One row per gate, who signed and when. This is your evidence.
IMPORTING TO SMARTSHEET
What imports cleanly | Migration Plan, Action Log, Change Requests, Field Mapping, Exception Sheet and Gate Sign-off are built for it: header on row 1, no merged cells, no formulas, real dates.
What does not | Overview, Reconciliation and Linkage Check use formulas. Smartsheet cannot import a cross-sheet formula. Import those only if you intend to rebuild the formulas as Smartsheet column formulas. They work as they are in Excel.
How to import | File, then Import, then Microsoft Excel. Tick "first row is a header". Smartsheet takes one sheet per file, so save the tab you want as its own workbook first.
Predecessors | The Predecessors column holds row numbers, which is what Smartsheet expects. Switch on Dependencies in Project Settings after import and it wires the chain up for you.
Hierarchy | Excel cannot carry indentation across. After import, select the tasks under each stage row and indent them once to rebuild the parent and child structure.
Column types | After import: Status to a dropdown (Not Started, In Progress, Done, Blocked, N/A), % Complete to a percentage, Owner to a contact column, Start and Finish to dates.
ABOUT THIS EXAMPLE
The engagement | Northwind Care Services moving from CareTrack 4.2 (legacy) to Meridian Care Platform. Seven years of records plus paper files. Kickoff 02 March 2026, currently mid cutover.
It is fictional | The client, both systems, every identifier and every number in here are invented to show the sheets working. No real engagement or client is described.
The Data Migration Toolkit — Michael Nocito

## Overview
Data Migration — Live Tracker
Client | Northwind Care Services
Moving from | CareTrack 4.2 (legacy)
Moving to | Meridian Care Platform
Scope | Seven years of records, plus paper
Migration lead | Migration Lead
Kickoff | 2026-03-02
Target go-live | 2026-08-03
Progress by stage
Stage | % Done
Stage 1 — Kickoff and Scope
Stage 2 — Profile the Source
Stage 3 — Map the Fields
Stage 4 — Clean and De-dupe
Stage 5 — The Dry Run
Stage 6 — User Acceptance Testing
Stage 7 — Freeze, Cutover, Bridge
Stage 8 — Hypercare and Close
Document Digitization (parallel)
Backfile (T plus 6 months)
OVERALL
This tab uses cross-sheet formulas, so it will not import to Smartsheet. See the Read Me.

## Migration Plan
# | Task ID | Task Name | Stage | Owner | Status | % Complete | Start | Finish | Duration (days) | Predecessors | Deliverable / Gate | Guide | Notes
| 1 | Stage 1 — Kickoff and Scope
1 | 1.1 | Internal handoff from Sales | Stage 1 — Kickoff and Scope | Sales / Account | Done | 100% | 2026-03-03 | 2026-03-04 | 2 |  | Scope, promises and stakeholders reviewed before the client sees you | migration-kickoff-scope
2 | 1.2 | Client kickoff meeting | Stage 1 — Kickoff and Scope | Migration Lead | Done | 100% | 2026-03-05 | 2026-03-05 | 1 | 1 | Agenda run in order; everyone knows who does what | migration-kickoff-scope
3 | 1.3 | Ask the four questions | Stage 1 — Kickoff and Scope | Migration Lead | Done | 100% | 2026-03-06 | 2026-03-09 | 2 | 2 | Success defined, contract signer known, data decision maker named, recovery plan agreed | migration-questions
4 | 1.4 | Agree a single point of contact | Stage 1 — Kickoff and Scope | Client PM | Done | 100% | 2026-03-10 | 2026-03-10 | 1 | 3 | One name, not an address book | migration-kickoff-scope
5 | 1.5 | Write the exclusion list | Stage 1 — Kickoff and Scope | Migration Lead | Done | 100% | 2026-03-11 | 2026-03-13 | 3 | 4 | What is NOT moving, in writing | migration-kickoff-scope
6 | 1.6 | Confirm source systems and access | Stage 1 — Kickoff and Scope | Client IT | Done | 100% | 2026-03-16 | 2026-03-18 | 3 | 5 | Read access granted, export method proven | migration-kickoff-scope
7 | 1.7 | Agree what happens to work created during the migration | Stage 1 — Kickoff and Scope | Client PM | Done | 100% | 2026-03-19 | 2026-03-19 | 1 | 6 | The gap is named before it opens | migration-cutover
8 | 1.8 | GATE — scope signed off | Stage 1 — Kickoff and Scope | Client PM | Done | 100% | 2026-03-20 | 2026-03-20 | 1 | 7 | Signed scope. Nothing else starts until this exists. | migration-kickoff-scope
| 2 | Stage 2 — Profile the Source
9 | 2.1 | Take the full initial export | Stage 2 — Profile the Source | Client IT | Done | 100% | 2026-03-23 | 2026-03-24 | 2 |  | Everything, not a sample | migration-profiling
10 | 2.2 | Run the seven checks | Stage 2 — Profile the Source | Migration Lead | Done | 100% | 2026-03-25 | 2026-03-31 | 5 | 9 | Row counts, blanks, duplicates, formats, ranges, orphans, encoding | migration-profiling
11 | 2.3 | Turn each finding into a decision | Stage 2 — Profile the Source | Migration Lead | Done | 100% | 2026-04-01 | 2026-04-03 | 3 | 10 | A finding with no decision is a finding you will meet again at cutover | migration-profiling
12 | 2.4 | Re-plan where profiling changed the estimate | Stage 2 — Profile the Source | Migration Lead | Done | 100% | 2026-04-06 | 2026-04-07 | 2 | 11 | Revised plan, with the reason attached | migration-scope-creep
13 | 2.5 | GATE — profiling report accepted | Stage 2 — Profile the Source | Client PM | Done | 100% | 2026-04-08 | 2026-04-08 | 1 | 12 | Client has seen the true state of their data | migration-profiling
| 3 | Stage 3 — Map the Fields
14 | 3.1 | Source to target mapping — records | Stage 3 — Map the Fields | Migration Lead | Done | 100% | 2026-04-09 | 2026-04-20 | 8 |  | Every field has a home, a rule and a reason | migration-field-mapping
15 | 3.2 | Document and metadata mapping | Stage 3 — Map the Fields | Migration Lead | Done | 100% | 2026-04-21 | 2026-04-24 | 4 | 14 | Documents are data too | migration-field-mapping
16 | 3.3 | Define the unique ID | Stage 3 — Map the Fields | Migration Lead | Done | 100% | 2026-04-27 | 2026-04-29 | 3 | 15 | One ID ties records and documents together | migration-field-mapping
17 | 3.4 | Decide on fields with nowhere to go | Stage 3 — Map the Fields | Client Data Owner | Done | 100% | 2026-04-30 | 2026-05-04 | 3 | 16 | Each one: move, drop or park, decided by the client | migration-field-mapping
18 | 3.5 | Client review of the map | Stage 3 — Map the Fields | Client PM | Done | 100% | 2026-05-05 | 2026-05-07 | 3 | 17 | Walked through, not emailed and hoped for | migration-field-mapping
19 | 3.6 | GATE — mapping signed off and version frozen | Stage 3 — Map the Fields | Client PM | Done | 100% | 2026-05-08 | 2026-05-08 | 1 | 18 | The signed copy is kept separate from the working copy | migration-file-hygiene
| 4 | Stage 4 — Clean and De-dupe
20 | 4.1 | Write the cleaning rules | Stage 4 — Clean and De-dupe | Migration Lead | Done | 100% | 2026-05-11 | 2026-05-14 | 4 |  | Rules, not one-off edits | migration-cleaning
21 | 4.2 | Preview every rule before applying it | Stage 4 — Clean and De-dupe | Migration Lead | Done | 100% | 2026-05-15 | 2026-05-19 | 3 | 20 | Row counts before and after, every time | migration-cleaning
22 | 4.3 | De-duplicate, deciding which record survives | Stage 4 — Clean and De-dupe | Migration Lead | Done | 100% | 2026-05-20 | 2026-05-25 | 4 | 21 | The client decides the survivor, not the loader | migration-cleaning
23 | 4.4 | Build the exception list | Stage 4 — Clean and De-dupe | Migration Lead | Done | 100% | 2026-05-26 | 2026-05-28 | 3 | 22 | Everything a rule cannot fix | migration-cleaning
24 | 4.5 | Client resolves exceptions | Stage 4 — Clean and De-dupe | Client Data Owner | Done | 100% | 2026-05-29 | 2026-06-05 | 6 | 23 | Decisions logged against each exception | migration-cleaning
25 | 4.6 | GATE — exception list closed or formally accepted | Stage 4 — Clean and De-dupe | Client PM | Done | 100% | 2026-06-08 | 2026-06-08 | 1 | 24 | Open exceptions are a decision, not an oversight | migration-cleaning
| 5 | Stage 5 — The Dry Run
26 | 5.1 | Load everything into the sandbox | Stage 5 — The Dry Run | Migration Lead | Done | 100% | 2026-06-09 | 2026-06-12 | 4 |  | The whole set. A sample proves nothing about volume. | migration-dry-run
27 | 5.2 | Run the four checks | Stage 5 — The Dry Run | Migration Lead | Done | 100% | 2026-06-15 | 2026-06-17 | 3 | 26 | Counts, control totals, links, spot fidelity | migration-dry-run
28 | 5.3 | Log every break and how the loader behaves | Stage 5 — The Dry Run | Migration Lead | Done | 100% | 2026-06-18 | 2026-06-22 | 3 | 27 | The loader log you will still be using next project | migration-dry-run
29 | 5.4 | Fix, reload and re-check | Stage 5 — The Dry Run | Migration Lead | Done | 100% | 2026-06-23 | 2026-06-29 | 5 | 28 | Repeat until the reconciliation is clean | migration-dry-run
30 | 5.5 | GATE — clean reconciliation in sandbox | Stage 5 — The Dry Run | Migration Lead | Done | 100% | 2026-06-30 | 2026-06-30 | 1 | 29 | Issues documented, not just fixed | migration-dry-run
| 6 | Stage 6 — User Acceptance Testing
31 | 6.1 | Choose testers who do the work daily | Stage 6 — User Acceptance Testing | Client PM | Done | 100% | 2026-07-01 | 2026-07-02 | 2 |  | Not managers. People who would notice. | migration-uat
32 | 6.2 | Give testers a script and real scenarios | Stage 6 — User Acceptance Testing | Migration Lead | Done | 100% | 2026-07-03 | 2026-07-07 | 3 | 31 | Ask a question, do not ask for a favour | migration-uat
33 | 6.3 | Run the UAT sessions | Stage 6 — User Acceptance Testing | Client SMEs | Done | 100% | 2026-07-08 | 2026-07-14 | 5 | 32 | Findings captured as they happen | migration-uat
34 | 6.4 | Triage UAT findings | Stage 6 — User Acceptance Testing | Migration Lead | Done | 100% | 2026-07-15 | 2026-07-17 | 3 | 33 | Fix, defer or explain, each one answered | migration-uat
35 | 6.5 | GATE — client signs off UAT | Stage 6 — User Acceptance Testing | Client PM | Done | 100% | 2026-07-20 | 2026-07-20 | 1 | 34 | Written sign-off from the people who tested | migration-uat
| 7 | Stage 7 — Freeze, Cutover and Bridge
36 | 7.1 | Agree and communicate the freeze window | Stage 7 — Freeze, Cutover and Bridge | Client PM | Done | 100% | 2026-07-21 | 2026-07-22 | 2 |  | Everyone knows when the old system stops taking work | migration-cutover
37 | 7.2 | Take the final delta export | Stage 7 — Freeze, Cutover and Bridge | Client IT | Done | 100% | 2026-07-23 | 2026-07-23 | 1 | 36 | Everything added since the initial export | migration-cutover
38 | 7.3 | Cutover, in order | Stage 7 — Freeze, Cutover and Bridge | Migration Lead | Done | 100% | 2026-07-24 | 2026-07-27 | 2 | 37 | Records, then documents, then links | migration-cutover
39 | 7.4 | Bridge import | Stage 7 — Freeze, Cutover and Bridge | Migration Lead | Done | 100% | 2026-07-28 | 2026-07-29 | 2 | 38 | The gap closed, not left for later | migration-cutover
40 | 7.5 | Post-load reconciliation | Stage 7 — Freeze, Cutover and Bridge | Migration Lead | In Progress | 50% | 2026-07-30 | 2026-07-31 | 2 | 39 | The same checks as the dry run, on production | migration-cutover
41 | 7.6 | GATE — go-live accepted | Stage 7 — Freeze, Cutover and Bridge | Client PM | In Progress | 50% | 2026-08-03 | 2026-08-03 | 1 | 40 | Numbers match, client accepts, together | migration-cutover
| 8 | Stage 8 — Hypercare and Close
42 | 8.1 | Agree the hypercare window before you need it | Stage 8 — Hypercare and Close | Client PM | In Progress | 30% | 2026-08-04 | 2026-08-04 | 1 |  | Length and route agreed in advance | migration-hypercare
43 | 8.2 | Log and resolve what surfaces | Stage 8 — Hypercare and Close | Migration Lead | In Progress | 30% | 2026-08-05 | 2026-08-25 | 15 | 42 | The long tail, tracked not absorbed | migration-hypercare
44 | 8.3 | Final reconciliation report | Stage 8 — Hypercare and Close | Migration Lead | Not Started | 0% | 2026-08-26 | 2026-08-28 | 3 | 43 | The proof the move was complete | migration-hypercare
45 | 8.4 | Internal results readout | Stage 8 — Hypercare and Close | Migration Lead | Not Started | 0% | 2026-08-31 | 2026-08-31 | 1 | 44 | What went well, what to change next time | migration-hypercare
46 | 8.5 | Handoff to Support | Stage 8 — Hypercare and Close | Support / CS | Not Started | 0% | 2026-09-01 | 2026-09-02 | 2 | 45 | So it lands warmly, with context | migration-hypercare
47 | 8.6 | GATE — project closed, handoff accepted | Stage 8 — Hypercare and Close | Support / CS | Not Started | 0% | 2026-09-03 | 2026-09-03 | 1 | 46 | Support owns it now, knowingly | migration-hypercare
| DD | Parallel — Document Digitization
48 | DD.1 | Audit paper volume, condition and scope | Parallel — Document Digitization | Client Data Owner | Done | 100% | 2026-03-06 | 2026-03-12 | 5 |  | How much paper, in what state | migration-field-mapping
49 | DD.2 | Select vendor and agree chain of custody | Parallel — Document Digitization | Client PM | Done | 100% | 2026-03-13 | 2026-03-24 | 8 | 48 | Who holds the records, and how it is proven | migration-field-mapping
50 | DD.3 | Define indexing metadata to match the map | Parallel — Document Digitization | Migration Lead | Done | 100% | 2026-03-25 | 2026-03-30 | 4 | 49 | Index to the target fields, not to what is convenient | migration-field-mapping
51 | DD.4 | Scan, OCR, index and QA | Parallel — Document Digitization | Scanning Vendor | Done | 100% | 2026-03-31 | 2026-05-11 | 30 | 50 | Digitized and indexed, ready to link | migration-field-mapping
52 | DD.5 | Day-forward scanning live at go-live | Parallel — Document Digitization | Scanning Vendor | Done | 100% | 2026-05-12 | 2026-05-12 | 1 | 51 | New paper never becomes new backlog | migration-cutover
| BF | Follow-on — Backfile (T plus 6 months)
53 | BF.1 | Backfile scanning continues | Follow-on — Backfile (T plus 6 months) | Scanning Vendor | Not Started | 0% | 2026-09-04 | 2027-01-07 | 90 |  | The historical paper, on contract | migration-hypercare
54 | BF.2 | Bridge import of historical documents | Follow-on — Backfile (T plus 6 months) | Migration Lead | Not Started | 0% | 2027-01-08 | 2027-01-14 | 5 | 53 | Loaded and linked by the same unique ID | migration-field-mapping
55 | BF.3 | Reconcile the backfile | Follow-on — Backfile (T plus 6 months) | Migration Lead | Not Started | 0% | 2027-01-15 | 2027-01-19 | 3 | 54 | Counts tie, no orphans | migration-pitfalls
56 | BF.4 | Decommission paper storage | Follow-on — Backfile (T plus 6 months) | Client PM | Not Started | 0% | 2027-01-20 | 2027-01-26 | 5 | 55 | The reason the project was funded | migration-hypercare

## Action Log
Action ID | Date raised | Source | Related Task ID | Action or decision needed | Owner | Status | Due | Resolution / notes
A001 | 2026-03-03 | Internal handoff | 1.1 | Sales to share the signed scope and the promises log | Sales / Account | Done | 2026-03-04 | Received. Two promises not in scope, logged as CR-01.
A002 | 2026-03-16 | Kickoff meeting | 1.6 | Client to send the legacy systems list and a sample export | Client IT | Done | 2026-03-18 | Export method proven.
A003 | 2026-03-06 | Kickoff meeting | 1.3 | Name the one person who decides on data questions | Client PM | Done | 2026-03-09 | Client Data Owner named. Saved a fortnight later.
A004 | 2026-04-01 | Profiling | 2.3 | Decide what happens to the 1,204 records with no date of birth | Client Data Owner | Done | 2026-04-03 | Move with the field blank. Flagged for post go-live cleanup.
A005 | 2026-04-01 | Profiling | 2.3 | Confirm records before 2019 are archive only and not migrating | Client PM | Done | 2026-04-03 | Confirmed. Cut the volume by about a third.
A006 | 2026-04-27 | Email | 3.3 | Decide the unique ID format: client number or record number | Client Data Owner | Done | 2026-04-29 | Client number. It is on the paper files too.
A007 | 2026-03-13 | Call | DD.2 | Approve the scanning vendor and the chain of custody document | Client PM | Done | 2026-03-24 | Approved. Custody log signed at each handover.
A008 | 2026-06-18 | Dry run | 5.3 | Loader silently truncates notes over 4,000 characters | Migration Lead | Done | 2026-06-22 | Split into a linked note record. Logged in the loader notes.
A009 | 2026-07-15 | UAT | 6.4 | Two testers report service type showing as blank on older records | Migration Lead | Done | 2026-07-17 | Free-text variant missed by the picklist map. Rule added, reloaded.
A010 | 2026-08-05 | Hypercare | 8.2 | Client asks for a count of documents loaded per year for their auditor | Migration Lead | Open | 2026-08-25

## Change Requests
CR ID | Date raised | Raised by | What is being asked for | In signed scope? | Impact on timeline | Impact on cost | Decision | Decided by | Date decided
CR-01 | 2026-03-05 | Sales / Account | Sales promised a custom field for referral source that is not in the target | No | None if done now | Half a day | Accepted. Small, and it was promised in the sale. | Client PM | 2026-03-09
CR-02 | 2026-04-09 | Client Data Owner | Migrate the scheduling history as well as the client and visit records | No | Plus 3 weeks | Plus 2 weeks effort | Two doors offered: move go-live, or defer to phase two. Client chose phase two. | Client PM | 2026-04-20
CR-03 | 2026-04-30 | Client SMEs | Keep the legacy note formatting exactly as it appears today | No | Plus 1 week | Plus 3 days | Declined. Explained what the target can and cannot hold, agreed plain text. | Client PM | 2026-05-04
CR-04 | 2026-05-26 | Client PM | Bring the go-live forward by one week to suit a board meeting | No | Minus 1 week | None | Declined. UAT sign-off would have been skipped. Reason put in writing. | Migration Lead | 2026-05-28

## Field Mapping
Source field | Source example | Target field | Transformation rule | Required? | Status | Signed off by | Date signed
client_name | Smith, John | First Name / Last Name | Split on the comma into two fields. Trim spaces. | Yes | Signed off | Client Data Owner | 2026-05-08
client_no | NW-4471 | Client ID (unique key) | Use as the unique ID. Ties records and documents together. | Yes | Signed off | Client Data Owner | 2026-05-08
dob | 01/02/1950 (text) | Date of Birth | Parse text to date as MM/DD/YYYY. Ambiguous values go to the exception list. | Yes | Signed off | Client Data Owner | 2026-05-08
status_cd | A | Client Status | A to Active, I to Inactive, D to Discharged. Anything else to the exception list. | Yes | Signed off | Client Data Owner | 2026-05-08
phone | (856) 555-1212 | Primary Phone | Strip formatting to digits only. Fewer than 10 digits to the exception list. | No | Signed off | Client Data Owner | 2026-05-08
svc_type | home aide / HHA / H.H.A. | Service Type (picklist) | Map every free-text variant to one picklist value. Variant list held separately. | Yes | Signed off | Client Data Owner | 2026-05-08
notes | free text, any length | Client Notes | Target truncates over 4,000 characters. Split the overflow into a linked note. | No | Signed off | Client Data Owner | 2026-06-29
referral_src | word of mouth | Referral Source (custom) | Custom field added under CR-01. | No | Signed off | Client PM | 2026-05-08
(paper file) | consent form, scanned | Document: type, date, author, client link | Indexed by the scanning vendor to the four target metadata fields. | Yes | Signed off | Client Data Owner | 2026-05-08
legacy_sched | visit schedule history | (not migrating) | Out of scope. Deferred to phase two under CR-02. | No | Excluded | Client PM | 2026-04-20

## Exception Sheet
Exception ID | Record ID | Field | Issue | Severity | Client decision | Status | Date resolved
E001 | NW-4471 | Date of Birth | Missing a required value | High | Supplied from the paper chart | Resolved | 2026-06-01
E002 | NW-4471 / NW-8123 | Client record | Possible duplicate: same name and date of birth | High | Confirmed a duplicate. Keep NW-4471, merge the visit history. | Resolved | 2026-06-01
E003 | NW-3290 | Primary Phone | Three digits, not a valid number | Low | Leave blank and correct after go-live | Resolved | 2026-06-01
E004 | NW-5567 | Service Type | Free-text value not in the picklist | Medium | Map to Home Health Aide | Resolved | 2026-06-03
E005 | D-2204 | Client link | Document has no matching client record | High | Re-indexed to NW-4471 by the vendor | Resolved | 2026-06-04
E006 | D-2210 | Scan quality | Paper scan is unreadable | Medium | Vendor to re-scan at a higher resolution | Resolved | 2026-06-05
E007 | NW-0099 | Date of Birth | Date is 02/03/1948, format ambiguous | Medium | Confirmed as 3 February from the paper chart | Resolved | 2026-06-02
E008 | 1,204 records | Date of Birth | Missing across a large batch | Medium | Accepted. Move blank, clean up after go-live. Logged as A004. | Accepted | 2026-04-03

## Reconciliation
Check | Source count | Target count | Difference | Result | When run | Notes
Client records | 1482 | 1482 |  |  | After cutover
Visit records | 58740 | 58740 |  |  | After cutover
Documents (scanned and native) | 6310 | 6310 |  |  | After cutover
Active clients | 913 | 913 |  |  | After cutover
Control total — balances | 284655 | 284655 |  |  | After cutover | Sum, not a count
Documents with a client link | 6310 | 6310 |  |  | After cutover | See Linkage Check
Run the same checks before the load and after it. A difference of zero on every row is the only pass. This tab uses formulas, so it will not import to Smartsheet.

## Linkage Check
Document ID | Document type | Client ID on the document | Found in records? | Result | Client IDs in the target
D-2201 | Consent form | NW-4471 |  |  | NW-4471
D-2202 | Care plan | NW-3290 |  |  | NW-3290
D-2203 | Referral | NW-5567 |  |  | NW-5567
D-2204 | Assessment | NW-4471 |  |  | NW-8123
D-2205 | Consent form | NW-8123 |  |  | NW-0099
D-2206 | Care plan | NW-0099
Column G is the list of client IDs that exist in the target. An orphaned document is a compliance problem, not a tidy-up job. This tab uses formulas, so it will not import to Smartsheet.

## Gate Sign-off
Gate | Stage | What is being signed | Signed by | Role | Date | Evidence held
G1 | Stage 1 — Kickoff and Scope | Scope, including the exclusion list | A. Reyes | Client PM | 2026-03-20 | Email, saved to 01-scope
G2 | Stage 2 — Profile the Source | Profiling report and the decisions taken from it | A. Reyes | Client PM | 2026-04-08 | Report v1.2, countersigned
G3 | Stage 3 — Map the Fields | The field map, version frozen | J. Okafor | Client Data Owner | 2026-05-08 | Map v3.0 signed. Working copy kept separate.
G4 | Stage 4 — Clean and De-dupe | Exception list closed or formally accepted | J. Okafor | Client Data Owner | 2026-06-08 | Exception sheet, 8 items, all answered
G5 | Stage 5 — The Dry Run | Clean reconciliation in the sandbox | Migration Lead | Migration Lead | 2026-06-30 | Reconciliation tab, all Pass
G6 | Stage 6 — User Acceptance Testing | UAT passed by the people who tested | A. Reyes | Client PM | 2026-07-20 | Sign-off sheet, 6 testers
G7 | Stage 7 — Freeze, Cutover, Bridge | Go-live accepted |  | Client PM |  | Pending. Post-load reconciliation runs to 03 August.
G8 | Stage 8 — Hypercare and Close | Project closed and handed to Support |  | Support / CS |  | Pending. Hypercare closes 03 September.