## Read Me
Migration Gate Sign-off Sheet
What a gate is | A stage you do not leave until somebody signs. Not a status update, not a meeting. A named person accepting that the stage is done.
Why it matters | Every argument late in a migration is about what was agreed earlier. This sheet is the answer to that argument, and it takes about a minute per stage to keep.
HOW TO USE IT
Fill in | Signed by, Role, Date signed, Evidence held, Status. They are the blue cells.
Evidence held | Where the proof lives, not a copy of it. "Email, saved to 01-scope" is enough. The point is that you can find it in six months.
Status | Not reached, Pending, Signed, Waived. Waived is a real answer, and it is a decision somebody made on purpose. Record who.
The example tab | The same eight gates, filled in for a fictional engagement, so the format is unambiguous.
THE EIGHT STAGES
In order | Kickoff and scope. Profile the source. Map the fields. Clean and de-dupe. The dry run. User acceptance testing. Freeze, cutover and bridge. Hypercare and close.
Written up | Each stage, what to do in it and what its gate is, at michaelnocito.github.io/analyst-prep-kit
THE REST OF THE TOOLKIT
Nine more tabs | This is one sheet from a set: the plan across all eight stages, an action log, change requests, field mapping, exceptions, reconciliation and a linkage check. Two workbooks, one blank and one worked through end to end.
Smartsheet | The full toolkit imports into Smartsheet: header on row 1, no merged cells, real dates and a predecessors column.
This sheet is fictional in its example only. The eight stages are the real method.
Michael Nocito

## Gate Sign-off
Gate | Stage | What is being signed | Signed by | Role | Date signed | Evidence held | Status
G1 | Stage 1 — Kickoff and Scope | Scope, including the exclusion list |  |  |  |  | Not reached
G2 | Stage 2 — Profile the Source | Profiling report and the decisions taken from it |  |  |  |  | Not reached
G3 | Stage 3 — Map the Fields | The field map, version frozen |  |  |  |  | Not reached
G4 | Stage 4 — Clean and De-dupe | Exception list closed or formally accepted |  |  |  |  | Not reached
G5 | Stage 5 — The Dry Run | Clean reconciliation in the sandbox |  |  |  |  | Not reached
G6 | Stage 6 — User Acceptance Testing | UAT passed by the people who tested |  |  |  |  | Not reached
G7 | Stage 7 — Freeze, Cutover, Bridge | Go-live accepted |  |  |  |  | Not reached
G8 | Stage 8 — Hypercare and Close | Project closed and handed to Support |  |  |  |  | Not reached

## Example — filled in
Gate | Stage | What is being signed | Signed by | Role | Date signed | Evidence held | Status
G1 | Stage 1 — Kickoff and Scope | Scope, including the exclusion list | A. Reyes | Client PM | 2026-03-13 | Email, saved to 01-scope | Signed
G2 | Stage 2 — Profile the Source | Profiling report and the decisions taken from it | A. Reyes | Client PM | 2026-04-01 | Report v1.2, countersigned | Signed
G3 | Stage 3 — Map the Fields | The field map, version frozen | J. Okafor | Client Data Owner | 2026-05-01 | Map v3.0. Working copy kept separate. | Signed
G4 | Stage 4 — Clean and De-dupe | Exception list closed or formally accepted | J. Okafor | Client Data Owner | 2026-06-01 | Exception sheet, 8 items, all answered | Signed
G5 | Stage 5 — The Dry Run | Clean reconciliation in the sandbox | Migration Lead | Migration Lead | 2026-06-24 | Reconciliation, every row Pass | Signed
G6 | Stage 6 — User Acceptance Testing | UAT passed by the people who tested | A. Reyes | Client PM | 2026-07-14 | Sign-off sheet, 6 testers | Signed
G7 | Stage 7 — Freeze, Cutover, Bridge | Go-live accepted |  | Client PM |  | Pending. Go-live acceptance meeting 03 August. | Pending
G8 | Stage 8 — Hypercare and Close | Project closed and handed to Support |  | Support / CS |  | Pending. Hypercare closes 03 September. | Pending